## Sprint Overview
SprintNumber | SprintDates | SprintDuration | TeamName | SprintGoal
Sprint 12 | 2025-09-01 to 2025-09-14 | 2 weeks, 10 business days | Alpha Team | Deliver user authentication + profile management features

## Team Capacity
TotalHoursPerPerson | HistoricalStoryPoints
40 | 25
Role | WorkingHours
Developer A | 40
QA B | 32
Designer C | 20

## Product Backlog
UserStorySummary | AcceptanceCriteria | Priority | Effort Estimate (StoryPoints)
As a user, I want to login so that I can access my account | Valid credentials -> success, invalid -> error message | High | 5
As a user, I want to register so that I can create an account | Email validation, password rules enforced | High | 8
As a user, I want to edit my profile | Update name, avatar, bio | Medium | 3

## Definition of Done
DefinitionOfDone
Code reviewed; Unit tests added; E2E tests pass; Deployed to staging; Documentation updated.

## Risks & Impediments
Risks & impediments
Third-party auth service downtime, Fallback to cached tokens / postpone non-critical flows

## Additional Comments
Comment
Coordinate with infra team for staging DB snapshot.